## Feuille 1
To this day
2 weeks with SDD
start date | end date | Tasks | Start Day | Duration in days
2019-10-15 | 2019-11-01 | Documentation and redifining the requirements | 0 | 17
2019-10-15 | 2019-10-29 | Redefining the requirements | 0 | 14
2019-10-15 | 2019-10-29 | Technical documentation | 0 | 14 | 5 weeks
2019-10-15 | 2019-10-29 | Task's lifecycle | 0 | 14
2019-10-29 | 2019-11-01 | Autosar documentation | 14 | 3 | 1 week
2019-10-29 | 2019-11-02 | Preparing the development environment | 14 | 4
2019-10-29 | 2019-10-30 | Install OS libraries | 14 | 1 | 1 week
2019-10-29 | 2019-10-30 | Install Python librairies and virtual environment | 14 | 1
2019-10-29 | 2019-10-30 | Install and compile OpenCV | 14 | 1
2019-11-01 | 2019-11-02 | Do the same for Raspberry Pi | 17 | 1 | 1 week
2019-10-31 | 2019-11-12 | Conception and modelisation of a hardware and software architecture (SDD) | 16 | 12
2019-10-31 | 2019-11-02 | Define the system's hardware architecture | 16 | 2
2019-10-31 | 2019-11-02 | Define the software modules of the system | 16 | 2
2019-10-31 | 2019-11-02 | Define the architecture between the software modules | 16 | 2
2019-11-02 | 2019-11-12 | Define the software components to use in each module | 18 | 10
2019-11-02 | 2019-11-12 | Define the test scenarios for each module | 18 | 10
2019-11-02 | 2019-11-12 | Define the integration tests scenarios | 18 | 10
2019-11-12 | 2019-12-17 | Implementation and test of the task's modules in computer | 28 | 35
2019-11-12 | 2019-12-03 | Code the different modules | 28 | 21
2019-11-19 | 2019-11-26 | Unit tests in the computer | 35 | 7
2019-11-19 | 2019-11-26 | Porterage of each module in the Raspberry Pi | 35 | 7
2019-11-26 | 2019-12-03 | Unit test for each module in the Raspberry Pi | 42 | 7
2019-11-26 | 2019-12-03 | Integration test in the computer | 42 | 7
2019-12-03 | 2019-12-17 | Integration test in the Raspberry Pi | 49 | 14
2019-12-17 | 2019-12-24 | Assuring data communication via Can bus | 63 | 7
2019-12-24 | 2020-01-30 | IHM | 70 | 37
2019-12-24 | 2020-01-30 | System test | 70 | 37